REQUEST FOR PROPOSAL

MARCH 13, 2026

TO PERFORM

Construction ENGINEERING SERVICES

CRITICAL pATH & sCHEDULING Review ONLY

FOR Project

6-297(014)000 PCN 24115

GRAND FORKS – INTERSECTION ND 297 AND 42ND ST

ronald J. henke, pe

DIRECTOR

NORTH DAKOTA DEPARTMENT OF TRANSPORTATION

PROPOSALS MUST BE DELIVERED TO

CHAD TAYLOR

ENVIRONMENTAL AND TRANSPORTATION SERVICES DIVISION

By

12:00 PM Central Time March 20, 2026

REQUEST FOR PROPOSAL (RFP)

PROJECT OVERVIEW

The North Dakota Department of Transportation (NDDOT) is requesting one qualified engineering consultant to perform project schedule review and Critical Path Method (CPM) analysis for:

6-297(014)000 PCN 24115

Work Type: Reconstruction

Location: Grand Forks, Intersection of ND 297 and 42nd Street

Bid Opening: March 13, 2026

Proposing firms must be qualified for Construction Engineering services and have demonstrated experience reviewing CPM schedules on highway or transportation projects. Project personnel must have expertise in CPM scheduling, delay analysis, and construction sequencing. All analyses shall follow generally accepted scheduling analysis best practices.

The NDDOT intends to execute one cost plus fixed fee contract requiring monthly billings per project with the selected consultant. The NDDOT reserves the right to assign work in phases and have the selected consultant perform any additional work not initially assigned. Project work items may be added or removed from the contract by work authorization or supplement agreement.

Services will be performed on an as-needed basis throughout the duration of the project as requested by the Engineer. Review durations and submission timelines shall align with the project schedule, and generally, consultants will allow 14 days for the review and/or approval of project deliverables by the NDDOT. All deliverables must be submitted to allow time for approval from the NDDOT and all appropriate agencies. The NDDOT is not responsible for added cost or lost time for the rework of the project deliverables.

Because the services are estimated to not exceed $300,000, this RFP is a seven-day advertisement.

Interviews will be conducted tentatively 10 days from the due date of this proposal.

Attached to the RFP is the Risk Management Appendix.

SCOPE OF SERVICES

Schedule Compliance Review

Review project schedules to verify that milestones, constraints, and deliverables are properly incorporated. Review baseline, updated, and revised CPM schedules for compliance with:

- Contract requirements and technical specifications

- Applicable scheduling standards and CPM best practices

- Required coding structures, calendars, activity durations, and logic

Identify and validate critical path(s) in the Contractor’s submitted schedules. Assess the reasonableness and continuity of critical path logic. Evaluate float values and identify excessive or artificial float.

Evaluate activity sequencing, logic ties, and use of lags and leads. Identify missing logic, open ends, or inappropriate constraints. Assess constructability and alignment of the schedule with the planned means and methods.

Review schedule updates for accuracy according to project progress, appropriate status of activities and remaining durations, and consistency with field observations and progress reports. Evaluate updated schedules against the baseline schedule and analyze the critical path changes over the project duration.

Assess the effects of change orders, delays, and differing site conditions to the overall schedule. Provide input for project decisions from a scheduling perspective (ex. time extension recommendations).

Attend project meetings as requested by the Engineer.

Provide written schedule review summary reports for baseline, updated/revised schedule, and time impact analysis that identify schedule compliance issues and/or critical path changes. Include schedule mark-ups, comment logs, narratives, and correspondence files as applicable.

The Consultant’s services do not include development of the Contractor’s CPM schedule, means and methods determination, or legal opinions regarding claims or disputes.

PROJECT PHASING

Preconstruction: Phase I shall, as applicable, include but not be limited to attending the preconstruction meeting, mobilization, initial construction administration work, if needed, and developing an NDDOT approved scope of work and hours for Phase II based on the contractor’s schedule and proposed method of operations.

The Engineer will have 14 days, from the date that the preconstruction meeting is completed to secure an approved scope of work and hours for Phase II. A preliminary scope of work and hours for Phase II shall be provided by the firm within 7 days of completion of the preconstruction meeting.  Pending NDDOT approval of the Phase II scope of work and hours completed in Phase I, the NDDOT may authorize the Engineer to perform Phase II and any additional work not currently assigned or completed in Phase I.

Construction: Phase II shall include, as applicable, construction engineering and administration through construction operations. Phase II will be considered complete upon final inspection and project acceptance by the NDDOT’s District Engineer and by the FHWA.  Phase II may also include developing an NDDOT approved scope of work and hours for Phase III if needed.

Dispute Resolution: Phase III shall, as applicable, include but not be limited to activities addressing extended contract dispute resolution resulting in arbitration.

PROJECT SUBMITTALS

Proposing firms must provide software for analyzing CPM schedules as submitted by the Contractor.

All design and project data will become the property of the NDDOT upon completion of the final submittal. Generate all project information in the following formats and standards:

•	MS Word and MS Excel

•	MicroStation 24.00.02.62

•	OpenRoads Designer 24.00.02.022

•	NDDOT CADD Manual

•	Microsoft “Project”

•	NDDOT Preliminary Surveys Manual requirements

•	NDDOT Design Manual and Plan Preparation Guide Website

•	NDDOT Right of Way Manual

•	Adobe Acrobat (standard or compatible)

All project submittals must follow WCAG 2.1, Level AA compliance according to the Americans with Disabilities Act (ADA) Title II.

DRONES

The American Security Drone Act of 2023 (ASDA) and OMB Memorandum M-26-02ll prohibits the use of drones manufactured by foreign companies on Federal Aid projects. Drone platforms, payloads, ground control systems, communications equipment, and related technologies used must be compliant with NDAA Section 889 restrictions. Documentation of compliance may be requested by the Department.

EVALUATION AND SELECTION PROCESS

Consultants interested in performing the work must submit one electronic copy in PDF format prior to the date and time listed on the cover of this RFP. Late proposals will not be considered.

Submit proposals by email to Chad Taylor cataylor@nd.gov with copies to Joy Glasoe jglasoe@nd.gov.

Each proposal must contain a cover letter signed by an authorized officer who can sign contracts for the consultant. Include the email addresses of these individuals. The pages of the cover letter will not be counted as a part of the pages.

The proposal pages shall be numbered and must be limited to five pages in length. Proposals that exceed the page length requirement will not be considered. This section should contain your approach and project specific plan.

The consultant’s proposal shall include an appendix. The appendix may include updated Federal form 330 if you do not have one on file with CAS. The pages in the appendix will not be counted as a part of the pages. The appendix shall include the following in this order:

Appendix A

Include a proposed work plan and project schedule with milestone of activities through project completion.

Appendix B

A staffing plan identifying the key project personnel (including titles, education, and work experience) and the respective roles and responsibilities for the project.

Appendix C

Project Specific QC/QA Plan including check lists, persons, responsibilities, proposed submittals and reviews, and DOT response timelines. The QC/QA Plan will be reviewed by the NDDOT and become part of the project after the contract has been signed.

Appendix D

Subconsultants and associated activities to be completed by the subconsultants. Attach proposed sublet form SFN 60232 for each sub at the end of this section.

Each proposal will be evaluated by a selection committee consisting of NDDOT staff members and/or representatives. The NDDOT reserves the right to limit the interviews to a minimum of three consultants whose proposals most clearly meet the RFP requirements. Consultants not selected to be interviewed will be notified in writing.

Selection will be based on the following weighted criteria:

| 10% | i. Past performance |
| --- | --- |
| 15% | ii. Ability of professional personnel |
| 10% | iii. Willingness to meet time and budget requirements |
| 05% | iv. Location |
| 10% | v. Recent, current, and projected workloads of the persons/consultants |
| 15% | vi. Related experience on similar projects |
| 10% | vii. Recent and current work for the agency |
| 25% | viii. Project understanding, issues, and approach |

Weights for each criterion are assigned independently for each specific project by CAS and the

Project Technical Representative. Maximum total weight is 100 points.

Shortlisting

Depending on the amount of interest for this solicitation, proposals may be subject to shortlisting. Following a review and evaluation of submitted proposals, the top three aggregate scorers will automatically have an interview, and additional firms may be invited to interview depending on point separation or natural breaks in aggregate scoring. Scoring categories match those stated previously. All firms that responded to the advertisement will be notified of the shortlisting determination and the reasons of the committee for selecting those to be interviewed. Shortlist scoring is independent of the interview scoring.

REQUEST TO SUBLET

Subconsultants that have been contacted and agree to be listed on the prime consultant’s project proposal must submit one copy of SFN 60232, Proposed Subconsultant Request to be attached to the proposal. This form is used for informational purposes only.

Prime consultants shall include a SFN 60233, Prime Consultant Request to Sublet form for each subconsultant prior to execution of the contract. The form assures that the contract between the prime consultant and all subconsultants contains all the pertinent provisions and requirements of the prime contract with the NDDOT.

*CIVIL RIGHTS

The North Dakota Department of Transportation, in accordance with the provisions of Title VI of the Civil Rights Act of 1964 (78 Stat. 252, 42 U.S.C. §§ 2000d to 2000d-4) and the regulations, hereby notifies all bidders that it will affirmatively ensure that any contract entered into pursuant to this advertisement, disadvantaged  business enterprises will be afforded full and fair opportunity to submit bids in response to this invitation and will not be discriminated against on the grounds of race, color, or national origin in consideration for an award.

*Title VI/Nondiscrimination and ADA

Title VI assures that no person or group of persons may, on the grounds of race, color, national origin, sex, age, or disability, be excluded from participation in, be denied the benefits of, or be otherwise subjected to discrimination under any and all programs or activities administered by the Department.  For information regarding Title VI, see the Title VI/Nondiscrimination and ADA Program at 2025-Title_VI_Nondiscrimination_and_ADA_Program_Implementation-Plan.pdf

*These requirements apply to every consultant on the project including every tier of subconsultant. It is the consultant’s or subconsultant’s responsibility to include these two paragraphs in every subcontract.

AUDIT

Consultants proposing to do work for the NDDOT must have an approved audited rate that is within 12 months of the close of the consultant’s fiscal year. Consultants that do not meet this requirement will not qualify to propose or contract for NDDOT projects until the requirement is met. Consultants that have submitted all the necessary information to the NDDOT and are waiting for the completion of the audit will be qualified to submit proposals for work. Information submitted by a consultant that is incomplete will not qualify. Out of state consultants can submit a current accepted Federal Audit Regulation (FAR) audit rate from a cognizant agency. Under certain conditions NDDOT may offer a Safe Harbor Rate of 110% to consultants that do not have a compliant rate.

PROMPT PAYMENT

Consultants will be required to make prompt payment to subconsultants as required by 49 CFR 26.29. The consultant must make payment to all subconsultants within thirty (30) calendar days from receipt of payment from the State. Such payment must be certified by the Consultant by submittal of the subsequent Consultant Contract Billing Form to the State. The State may withhold subsequent payment(s) to the Consultant if any subconsultants have not been paid for work satisfactorily completed.

RIGHT OF REJECTION

The North Dakota Department of Transportation reserves the right to reject any or all proposals.

DISCLOSURE OF PROPOSAL

At the conclusion of the selection process, the contents of the shortlisted proposals will be subject to North Dakota's Open Records Law and may be open to inspection by interested parties. Any information included in the proposal that the proposing party believes to be a trade secret or proprietary information must be clearly identified in the proposal.  Any identified information recognized as such and protected by law may be exempt from disclosure.

RISK MANAGEMENT FOR PROFESSIONAL SERVICES

The Risk Management Appendix/Addendum will be incorporated into the agreement between NDDOT and the consultant.

Consultants must provide a proper Certificate of Insurance within 15 days of notification of selection.

CONSULTANT EMAIL CONTACTS

If necessary, please update contact information for receiving emails and phone calls.