## Table 1
Overall Project Progress – PHASE II (Preliminary Engineering & Environmental)
Description | Project Status* | % Complete |  |  | Projected Start Date | Original NDDOT Milestones** | Actual Completion Date | Anticipated Milestones Date | Explanation | Plan to Correct
|  | Period Start | Period End | Period Next
Traffic Data | Complete | 100 |  |  |  | 2020-07-22 | 2022-09-09
Field Review | Complete | 100 |  |  |  | 2021-07-01 | 2021-07-12
Solicitation of Views | Complete | 100 |  |  |  | 2022-01-15 | 2022-02-17
Management Presentation | On Schedule | 0 | 0 | 0 | 2022-10-31 | 2022-11-01 |  | 2022-11-16
Public Input Meeting #1 | Complete | 100 |  |  |  | 2022-12-01 | 2022-06-01
Public Input Meeting #2 | On Schedule | 0 | 0 | 0 | 2022-10-31 | None |  | 2022-12-06
Land Use Workshop | Complete | 100 |  |  |  | None | 2022-01-19
Alternatives Brainstorming Workshop | On Schedule | 100 |  |  |  | None | 2022-04-25
Alternatives Assessment Workshop | On Schedule | 0 | 10 | 50 |  | None |  | 2022-09-26
Traffic Operations | Behind Schedule | 60 | 65 | 70 |  | 2022-09-01 |  | 2022-11-18
Preliminary Engineering | On Schedule | 70 | 75 | 80 |  | None |  | 2023-01-13
Wetland Delineation-Field | Complete | 100 |  |  |  | 2021-11-15 | 2022-07-22
Wetland Jurisdictional Request | Complete | 100 |  |  |  | 2022-01-15 | 2022-09-01
Jurisdictional Determination | Behind Schedule | 0 | 5 | 10 |  | 2022-02-15 |  | 2022-11-01
Class III Cultural Resources Inventory | Behind Schedule | 85 | 90 | 100 |  | 2022-06-01 |  | 2022-09-02
Section 106 Compliance | Behind Schedule | 0 | 0 | 10 |  | 2022-09-01 |  | 2022-11-01
Noise Analysis | Behind Schedule | 10 | 15 | 15 |  | 2022-08-01 |  | 2022-11-16
Phase I ESA | On Schedule | 0 | 0 | 0 | 2022-10-17 | none |  | 2022-12-01
Draft Documented CATEX | On Schedule | 0 | 5 | 10 |  | 2023-01-15 |  | 2023-01-15
Interstate System Access Change Request | On Schedule | 0 | 0 | 0 | 2022-12-19 | 2023-03-15 |  | 2023-03-15
Documented CATEX | On Schedule | 0 | 0 | 0 | 2023-01-30 | 2023-02-15 |  | 2023-02-15
Categorical Exclusion | On Schedule | 0 | 0 | 0 | 2023-03-06 | 2023-04-15 |  | 2023-04-15
Aerial Survey | Complete | 100 |  |  |  | 2022-05-01 | 2022-05-17
Ground Truthing | Complete | 100 |  |  |  | None | 2022-08-18
Survey Transmittal | Behind Schedule | 20 | 25 | 30 |  | 2022-05-01 |  | 2022-11-01
Description | Project Status* | % Complete |  |  | Projected Start Date | Original NDDOT Milestones** | Actual Completion Date | Anticipated Milestones Date | Explanation | Plan to Correct
|  | Period Start | Period End | Period Next
Preliminary Utility Coordination | Behind Schedule | 50 | 50 | 50 |  | 2022-02-01 |  | 2022-11-01
Preliminary Utility Engineering | Behind Schedule | 10 | 10 | 10 |  | 2022-10-01 |  | 2022-12-02
* Based on NDDOT Chapter 1-04.02 PSR Reporting **Based on Milestone Report dated 12/30/2021